## RHQ
BLDG # | Name | Purpose/Function | BLDG Manager (POC) | CAT Code | ISR Code | Grid Coordinate | Occupancy | Issues | Fix | S/O-IJO # | Notes | Map | IJO Tracker | S/O Tracker
2931 | RHQ | Office | P: MAJ Vikhrov 706-545-7637 / ALT: LT William Miller 706-545-5193 |  |  |  |  | 1.HVAC System not adequate | 1. 09SEP19/ DPW doing case study to find solution | 18130 | Houses: CMD Cell, RS1, RS2, RS3, RJAG, RS8, RENG | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Irrigation System inop | 2. 09SEP10/ Contractor could not find main water line, may have to put out to bid again | 18068
[8 empty] | 3. Remove Comms Tower | 3. Unit will have to fund | 18072
[8 empty] | 4. Pain and Carpet Room 113 | 4. Unit will have to fund/ waiting to submit to O-5 Board FSRM | 18080
[8 empty] | 5. Create Handicapped Entrance | 5. TIYA can't fund until FY20/ Estimate $8,184 | 18112
[8 empty] | 6. Remove Staff Duty Desk | 6. Deffered until FY20 not L/H/S | 18113
[8 empty] | 7. RCO Entry Way | 7. Work estimated? Waiting to submit to FSRM Board | 18137
[8 empty] | 8. Install White Boards into S3 | 8. Deffered until FY20 not L/H/S | 18138
[8 empty] | 9. S6 remove wall mounts for monitors | 9. Waiting on approval | 18149
[8 empty] | 10. Install Walls in RM 240 (S3) | 10. Unit will have to fund | 18075
2932 | RHHC | Office | P: 1LT Dunn matthew.p.dunn.mil@socom.mil / ALT: CPT Custer 706-545-3183 |  |  |  |  | 1. Bathroom Shower Head not working | 1. Called in Service Order 09SEP19 | 741255 | Houses: RHHC CMD team, and support staff | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Ceiling Tiles broken/cracked from water damage | 2. Called in Service Order 09SEP19 | 741258
2386 | RLOC/ RIF | Office | P: Ms. Gaston 706-545-8008 / ALT: |  |  | 32.348785, -84.983940 |  | 1. Clean Plastic Air Ducts in back room | 1 Work Order Submitted | 18095 | Houses: RLOC/RIF/RS4 | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Redo fire suppression on I-Beams | 2 Work Order Submitted | 18096
[8 empty] | 3. Repaint I-beams | 3 Work Order Submitted | 18097
[8 empty] | 4. Clean and Repair Gutter | 4 Work Order Submitted | 18098
[8 empty] | 5. Clean outside lights and replace with LED | 5. Deffered not L/H/S | 18099
[8 empty] | 6. Pressure wash building | 6. Deffered not L/H/S | 18100
[8 empty] | 7. Replace Floor tiles | 7. Deffered not L/H/S | 18101
[8 empty] | 8. Additional Fountain needed on second floor | 8. Deputy RENG stated no additional construction can happen for one year AUG19 | 18142
[8 empty] | 9. Additional Bathrrom needed on second floor | 9. Deputy RENG stated no additional construction can happen for one year AUG20 | 18142
[8 empty] | 10. Install pedestrian access gate with lock | 10. Deffered not L/H/S | 18123
[8 empty] | 11. Repair Forklift | 11 Work Order Submitted | 18144
[8 empty] | 12. Install new locks for doors on RIF | 12. Work order submitted 11SEP19 | 18150
2830 | CCT/RMED | Medical | P: SFC Conaway 708-545-5766 / ALT: SSG Pate 706-545-7435 |  |  | 32.343321, -84.975964 |  | 1. Repalce Windows | 1. Waiting for estimate/ FSRM | 18108 | Houses: Care Coalition Team in charge of helpin wounded Rangers with transition back to statside | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Install Security Syetem | 2. Waiting for funding | 18141
2863 | Future CEMA Vehicle Shop, currently used by LRC | Car Shop | N/A | [7 empty] | Currently on borrow to installation for SSA till 2021 | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2300 | Fires | Training Facility | P: SFC Boswell joshua.b.boswell@socom.mil / ALT: CPT Ruestche james.j.ruetsche@socom.mil |  |  |  |  | 1. Conduct Power Study | TBD | 18127 | Houses: RHQ Fires section | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Conduct HVAC Study | TBD | 18128
[8 empty] | 3. Remove shelving | TBD
[8 empty] | 4. Move Domes into Facility | TBD
[8 empty] | 5. Build flooring for workspace | TBD
2839 | RMIB | Office | P: MAJ Vikhrov 706-545-7637 / ALT: LT William Miller 706-545-5193 |  |  |  |  | 1. Mold in cornner office | 1. Work order submitted |  | Houses: RFM, RENG, RCHAP, PAO, TDY, RSTB/HHC | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Carpet torn | 2. Work order submitted
[8 empty] | 3. Rain gutter missing | 3. Work order submitted
[8 empty] | 4. Basement door broken | 4. Service order submitted
2933 | RMED | Medical | P: SFC Conaway 706-545-5766 / ALT: SSG Pate 706-545-7435 |  |  |  |  | 1. Shower head and towel rack install | 1. Work order submitted 22JUL19 | 18135 | Houses: RMED staff | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2835 | RPEC | Medical | P: SFC Vargas 706-545-5969 / ALT: SGT Isley 706-544-7396 | [7 empty] | Houses: RPSCYH | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2917 | HPTC (gym) | Gym | P: Nick O'Brien 706-626-2912 / ALT: David Meyer 706-545-4866 |  |  |  |  | 1. Wall has holes in back side by Scrolls | 1. Deffered not L/H/S | 18133 | Houses: HPTC staff | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Additional lights needed by office area | 2. Deffered not L/H/S | 18133
[8 empty] | 3. Network Switch to replace old one | 3. Waiting on contractor to buy new rack to emplace new switch
2831 | EMPTY/RSTB | Barracks | P: 1LT Schneider 706-545-1943 / ALT: 1LT Roth 706-545-1943 |  |  |  |  | 1. In need of major renovations |  |  | Slotted for RSTC/RASP | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2836 | EMPTY/RSTB | Barracks | P: 1LT Schneider 706-545-1943 / ALT: 1LT Roth 706-545-1943 |  |  |  |  | 1. Needs a Fire Suppression System | 1. Work order submitted 03DEC18 | 18071 | Slotted for RSTC/RASP | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2837 | RSTB/ Trasient Barracks | Barracks | P: 1LT Schneider 706-545-1943 / ALT: 1LT Roth 706-545-1943 |  |  |  |  | 1. In need of major renovations |  |  | Houses: Transist PLT from RSTC | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2838 | EMPTY/RSTB | Barracks | P: 1LT Schneider 706-545-1943 / ALT: 1LT Roth 706-545-1943 |  |  |  |  | 1. In need of major renovations |  |  | Slotted for RSTC/RASP | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2929 | RIOC | Office | P: SFC Donjte 706-626-1291 / ALT: CW2 Dansby 706-545-4462 |  |  |  |  | 1. Partician Walls for additional offcies | 1. Work Scheduled 10SEP19 | 18063 | Houses: RS2 & RMIB | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
[8 empty] | 2. Repair Drainage in parking lot | 2. FEB19 walkthough with SME | 18070
[8 empty] | 3. Install 5 Parking signs | 3. S/O called in 5FEB19
2825 | EMPTY | Office | N/A | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2896 | EMPTY | Office | N/A | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2897 | EMPTY | Office | N/A | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
2824 | EMPTY | Office | N/A | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Installation Job Orders.one | 1. RENG Continuity File\RENG One Note_ALL THINGS RENG\Service Orders.one
Scheduled for Demolition
Scheduled for Demolition
Scheduled for Demolition
Scheduled for Demolition
Scheduled for Demolition

## RMIB
BLDG # | Name | Purpose/Function | BLDG Manager (POC) | CAT Code | ISR Code | Grid Coordinate | Occupancy | Issues | Fix | S/O-IJO # | Notes | Map
2394 | Old/ CEMA | Office | 1LT Adams (CEMA XO) 706-545-2168 / 1LT Shinnick (CEMA OPSO) 706-545-2168 | [7 empty] | Currently house CEMA (Cyber Electro Magnetic Activites Co.) in a temp trailer- scheduled to move to Bldg 334 | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
334 | New/ CEMA | Office | 1LT Adams (CEMA XO) 706-545-2168 / 1LT Shinnick (CEMA OPSO) 706-545-2169 | [7 empty] | Currently being renovated with open storage security measure, wall to wall carpeting, and a incenerator | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2403 | TUAV/ Hangar | Office | SFC Albaugh 706-545-9811 / 1LT Oliver 706-545-4130 | [7 empty] | Currently waitinig on furniture contract, and network installation | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2930 | MICO | Medical | 1LT McFadden 706-545-0715 / SSG Williams 706-545-0715 | [7 empty] | Houses: ASPS/GIS/HUMINT/Trainig Room/Targeting | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2839 | RMIB HQ | Office | 1LT Chris Bascomb Black: 706-545-5193 Red: 545-5193 Cell: 201-956-1065 | [7 empty] | Houses: ASPS/GIS/HUMINT/Trainig Room/Targeting | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf

## RSTB
BLDG # | Name | Purpose/Function | BLDG Manager (POC) | CAT Code | ISR Code | Grid Coordinate | Occupancy | Issues | Fix | S/O-IJO # | Notes | Map
278 | RDP | Office | SFC Beauchamp, Robert 706-545-6743 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
334 | RSTB HHC | Office | SFC Celmer, Clayton 706-545-7466 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2408 | Rigger Facility | Office | SFC Pratt, Michael 706-545-8381 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2641 | RSTB Barracks | Barracks | SFC Clemer, Clayton 706-545-7466 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2831 | RSTC PENDING REMODEL ~FY21-22 | Barracks | 1LT Glatz, Richard 706-545-7070 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2832 | RSTC | Barracks | SSG Hardesty, Kevin 706-545-3777 |  |  |  |  | USACE Study is needed to determine the cause of the issue. Bring HVAC SME to determine mulfunction. Agreed to pay for the outside AC sourse. Need Memo to install temporary AC. |  |  |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2833 | RSTC | Barracks | SSG Hardesty, Kevin 706-545-3777 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2834 | RSTC | Barracks | SSG Hardesty, Kevin 706-545-3777 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2836 | RDP PENDING | Barracks | 1LT Glatz, Richard 706-545-7070 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2837 | Transitions | Barracks | SSG Akkerman, Daniel 706-545-8910 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2838 | Transitions | Barracks | SSG Dearman, Kyle 912-695-3184 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2848 | PBO | Office | Mr. Robinson, Floyd 706-545-1277 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2851 | TSD Storage | Storage | 1LT Glatz, Richard 706-545-7070 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2852 | RSTB HQ | Office | 1LT Glatz, Richard 706-545-7070 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2853 | RCC East Side | Office | CPT Bordes, Ian 706-626-2725 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2853 | RRC West Side | Office | CPT Snyder, Ian 706-545-6838 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2854 | RSTB MOPO | Car Shop | SSG Trebat, Vincent 706-545-6752 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2858 | Deployment Storage | Storage | 1LT Glatz, Richard 706-545-7070 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf

## 3-75
BLDG # | Name | Purpose/Function | BLDG Manager (POC) | CAT Code | ISR Code | Grid Coordinate | Occupancy | Issues | Fix | S/O-IJO # | Notes | Map
2643 | Smith Gym Barracks | Gym | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [7 empty] | Will turn over to post when 2939 and 2940 renovations are complete (FEB-MAR 2020). | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2907 | 3/75 Kennels | Office | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2910 | A, B, C, E Co COFs | Office | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | B Co wants to create a secured "maker's space" | Install Workshop Cage in B Co COF | HK160289J |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
[8 empty] | Female Rangers will not have a shower space in the COFs | Install Shower in B Co COF / Option for All COFs | HK160369J
[8 empty] | Need new keys for rooms in C Co COF | Re-Key Rooms in C Co COF | HK160389J
2912 | Commo Shop | Office | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | A/C goes out a lot and is at end of life | Replace HVAC unit |  |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2913 | PBO Warehouse | Office | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | A/C goes out a lot and is at end of life | Replace HVAC Unit | HK160008J |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2914 | Maintenance Shop | car shop | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | Motorpool entrance not in compliance with security reqts | Install Speed Bumps at Motorpool Gates | HK160359J |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2934 | Dawson Barracks - E Co & HHC | barracks | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2935 | Dawson Barracks - D Co | barracks | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2936 | Dawson Barracks - C Co | barracks | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2937 | Dawson Barracks - B Co | barracks | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2938 | Dawson Barracks - A Co | barracks | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | Do not have keys to several rooms | Re-Key Barracks Rooms | HK160399J |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2939 | Dawson Barracks - Overflow | barracks | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [7 empty] | Currently under renovation. Work is complete. Building turnover pending furniture delivery on 15 OCT. | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2940 | Dawson Barracks - Overflow | barracks | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [7 empty] | Currently under renovation. Estimated turnover date is FEB/MAR 2020. | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2941 | Gym | Gym | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | Want to mount TVs in gym | Mount Indoor / Outdoor TVs in Gym (DPW approved for GPC, LPR submitted) | HK160299J | Renovation pending inspection of fire alarm and final inspection. Pre-final scheduled for 19SEP19 at 1000. Other IJOs pending completion of renovation. | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
[8 empty] | Renovation did not remove carpet sections from cardio room | Remove Carpet / Polish Floor | HK160379J
2942 | PT Clinic | Medical | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | Needs new HVAC | HVAC renovation pending contract award. | RPPB project | Pending contract award. Renovation will upgrade the HVAC, demo and install internal walls to optimize the space, and install a community kitchen for barracks personnel to use. | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2943 | DFAC | Dining Facility | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | Inadequate grilling space | Construct Outdoor Grilling Space for DFAC | HK160329J | FSRM validated, money obligated, project assigned to TIYA project coordinator. Pending award of TIYA sub-contract. | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2944 | D Co COF | Office | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | Need laundry hook ups | Install Laundry Hookups in D Co/HHC COFs | HK160029J |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
2945 | HHC COF / BAS | Office | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 |  |  |  |  | Need laundry hook ups | Install Laundry Hookups in D Co/HHC COFs | HK160029J |  | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf
[8 empty] | Female Rangers need a locker room | Install Female Locker Room in HHC COF | HK160369J
2946 | BN HQ | Office | Zach T. Cohen 1LT, EN 3rd Battalion, 75th Ranger Regiment Battalion Engineer UNCLASS: zachary.t.cohen.mil@socom.mil JIANT: zachary.t.cohen@soc.smil.mil BLACK: (706) 545-7671 RED: (706) 545-5032 Cell: (303) 601-6420 | [8 empty] | MAPS\FB_Main_Post_Ranger_Regt_Footprint_map_image.pdf